## Slide 1: Control Risks
MEC-9
Outline
The domain of Monitoring & Controlling Risks
Processes of the Risk KA and the Control Risk Process
Role of Contingency and Management Reserves in the MEC of Risks
Some typical Risk MEC Situations
Readings
PMBoK, pages 349-354.
Rita, pages 88 & 431-443.
Lecture Notes.

## Slide 2: What is MEC of Risks? - 1/5
Tracking and reviewing Identified Risks and their Trigger conditions, for their validity and changes
Monitoring and controlling Residual and Secondary Risks
Identifying and analysing New Risks (Known Unknowns); preparing their contingency plans and allocating them Contingency Reserves (CR) … (Risks can be identified anytime during the project, along with plans for how to handle the newly identified risks)
Endeavouring, where possible, to convert threats (negative risks) into opportunities (positive risks)
Evaluating the effectiveness of the Risk Management Plan & risk processes:
"Are the risk management processes working?"
Tracking, reviewing, implementing & modifying Risk Response Plans:
"That plan no longer seems like it will work based on new information. Let's plan a different response."
Notes: Agile, Waterfall

## Slide 3: What is MEC of Risks? - 2/5
Collecting and communicating Risk Status to the Stakeholders (at the Project Review Meetings):
“Four identified risks occurred last month, and all risk response plans were implemented successfully. Next month we expect eight other risks to potentially occur. Risk reserves are still considered adequate for covering the identified risks on this project.” or
"Remember that one of the major risks on the project could occur next week"
Determining if Assumptions are still valid
Ensuring proper risk management procedures are being followed
Revisiting the Watch List to see if additional risk responses need to be determined:
"This change to the product scope might increase the impact of risk X, currently on our Watch List. Let's analyse it"
Notes: Agile, Waterfall

## Slide 4: What is MEC of Risks? - 3/5
Revisiting the High and Medium Risks and see if they can be de-escalated to the Watch List; see if Medium Risks need escalation to High:
“Though we had risk Y rated High, do we need to de-escalate it in view of the improved law and order situation in the country?”
Recommending corrective actions to adjust to the severity of actual risk events:
"This risk did not have the impact we expected, so let's adjust the contingency plan we are in the middle of implementing and change what we will do if the risk reoccurs”
Looking for any unexpected effects or consequences of risk events:
"We did not expect this risk to damage the construction site if the risk occurred. We need to decide how to fix the damage after we finish implementing the already agreed-upon contingency plan."
Notes: Agile, Waterfall

## Slide 5: What is MEC of Risks? - 4/5
Reevaluate risk identification, and qualitative and quantitative risk analysis when the project deviates from the baseline:
"The project cost is over the cost baseline (or over the schedule baseline). This implies we missed some major risks. Let's hold a risk identification session."
Controlling New Risks (Unknown Unknowns) as they occur; qualifying the risks; analysing reasons for their non-identification; initiating changes for Management Reserves (MR)
Updating risk management plan and project documents with approved changes and any relevant information from the WPD
Looking at the changes, including recommended corrective actions, to see if they lead to identifying more risks:
"We keep having to take corrective action related to this problem. Let's look at the root cause and identify any risks for the remaining part of the project that relate to the problem."
Notes: Agile, Waterfall

## Slide 6: What is MEC of Risks? - 5/5
Submitting Change Requests to integrated change control
Closing of Risks that are no longer applicable (to enable the team to concentrate on the risks that are still open)
Creating a database of risk data that may be used throughout the organisation on other projects
Performing variance and trend analysis on project performance data
Using CR and adjusting for approved changes
Monitoring, Reviewing & Controlling responsibilities entrusted to the Risk Owners (Risk Owners also propose/develop and implement Risk Response plans)
Updating the Risk Register
Notes: Agile, Waterfall

## Slide 7: Processes in the Risk Knowledge Area
Plan Risk Management
- Risk Management Plan
Identify Risks
- Risk Register
Process
Key Outputs
Perform Qualitative Analysis
-Risk Register update
Perform Quantitative Analysis
-Risk Register update
Plan Risk Responses
-Risk Register update
Control Risks
- WPI
- Change Request
Notes: Agile, Waterfall

## Slide 8: Control Risks Inputs & Outputs
Control Risks
PMP
PDs (w/a)
WPD*
OPA
Any Specific Input
PMP Updates
PD Updates
WPI**
OPA Updates
Any Specific Output
+
Change Request
Risk Mgt Plan
Risk Register (from Identify Risks)
*: from the Direct & Manage Project Work process
**: to the Monitor & Control process
Risk Register updated:
New Risks
Residual Risks
Secondary Risks
Other Changes ***
WPR (from Mon & Cont Proj Work)
X
***: changes to Risk Register contents resulting from implementation of Response Plans, Risk Reassessment, Risk Audits, Risk Reviews, etc
Notes: Agile, Waterfall

## Slide 9: WPD → WPI → WPR Flow Path Complete Model
Direct & Manage Proj Work
Control Scope
Control Schedule
Control Costs
Control Quality
Control Comm
Control Risks
Control Procurements
Control S/Holder Engagement
Validate Scope
WPD
WPIs
Monitor & Control Proj Work
Perform Integrated Change Control
Develop PMP
Manage Proj Team
Manage Comm
WPRs
Approved Change Requests
Project Documents Updates
Project Plan Updates
Notes: Agile, Waterfall

## Slide 10: Monitor & Control Risks Inputs
Input | Details
Project Risk Management Plan | How the Project Risks will be Monitored & Controlled
WPD | Status of Deliverables Schedule Progress Costs incurred
WPR | EV Data (including Forecasting Data) Variance Analysis
Risk Register | Key inputs for Risks monitoring & control: |  | 
 | Identified Risks Watch List Risk Responses | Residual Risks Risk Owners Risk Trigger | CR (Time & Cost)
Notes: Agile, Waterfall

## Slide 11: Monitor & Control Risks Outputs … 1/2
Output | Details
WPI | Results of Risk Audits Status of risks (possibility of their closure now or in near future) Assessment of Risks
Change Request | Corrective Actions Workarounds
Residual Risks | Risk remaining after the application of the Risk Response
New Risks | Risks not previously identified and hence not in the Risk Register
Risk Register Updates | Contents of the WPIs Results of implemented risk responses Residual Risk New Risks Closing of risks no longer applicable Details of what happened when risks occurred
Notes: Agile, Waterfall

## Slide 12: Monitor & Control Risks Outputs … 2/2
Output | Details
Project Management Plan Updates | Updates resulting from approved Change Requests
OPA Updates | Updated with: Risks & Risk Responses (appropriate contents of Risk Register) Checklists
Notes: Agile, Waterfall

## Slide 13: Monitor & Control Risks – Tools & Techniques … 1/2
Tools & Techs | Details
Risk Reassessments | Regular reassessment of risks involving, or resulting in: Identification of new risks Additional/iterative qualitative & quantitative analysis of previously identified risks, and/or of new risks Further risk response planning of previously identified risks, and/or of new risks
Risk Audits | Performed at a frequency and in a format spelt out in the Risk Management Plan, with the purpose of: Assessing the overall effectiveness of risk management processes on the project Examining the effectiveness of risk responses in dealing with the identified risks and their root causes
Workarounds | Unplanned responses developed to deal with: the occurrence of unanticipated events or problems (unknown unknowns) on a project the risks that had been accepted passively because of unlikeli-hood of occurrence and/or minimal impact, but have occurred
Notes: Agile, Waterfall

## Slide 14: Monitor & Control Risks – Tools & Techniques … 2/2
Tools & Techs | Details
Reserve Analysis | Throughout execution of the project, some risks may occur with positive or negative impacts on budget or schedule CR Reserve analysis checks how much reserve remains and how much might be needed for the amount of risk remaining at any time in the project
Variance and Trend Analysis | Trends in the project’s execution reviewed using Earned Value Analysis, other methods of project variance and Trend Analysis
Meetings | Project risk management is be an agenda item at periodic status meetings Amount of time required for that item will vary, depending upon the risks that have been identified, their priority, and difficulty of response The more often risk management is practiced, the easier it becomes Frequent discussions about risk make it more likely that people will identify risks and opportunities
Notes: Agile, Waterfall

## Slide 15: Monitoring & Control Actions in Execution Phase – 1/3
A previously identified Risk, budgeted with CR, has occurred
Implement the Risk Response Plan as devised and defined in the Risk Register Monitor Residual & Secondary Risks Use the CR set aside for the Risk Update the Risk Register
Situation
A New Risk, i.e. a risk not listed in the Risk Register, is identified or discovered
Monitoring & Control Actions
Analyse and qualify the risk, going through the process of Qualitative risk analysis, followed by Quantitative risk analysis if required, depending on the EMV Plan a Risk Response if EMV Med or High Allocate CR (unless it is decided to Accept the risk Passively in which case no CR will be allocated) Update Risk Register
Notes: Agile, Waterfall

## Slide 16: Monitoring & Control Actions in Execution Phase – 2/3
Situation
A previously identified Risk, not budgeted with CR (i.e. the Risk was Accepted Passively), has occurred or A New Risk, i.e. a risk not listed in the Risk Register and, therefore, not budgeted with CR, has occurred
Monitoring & Control Actions
Create a workaround (take corrective or preventive action, like Fast Tracking or Crashing if it is a problem with schedule) Adjust the project to accommodate or make up for the impact of the risk including resulting changes Look for any unexpected effects of the risk, particularly Secondary & Residual Risks Reevaluate the Identify Risk process (if New Risk) Update the Risk Register Use MR if approved and released by the management of the performing organisation
Notes: Agile, Waterfall

## Slide 17: Monitoring & Control Actions in Execution Phase – 3/3
Situation
A previously identified Risk, budgeted with CR, does not occur
Monitoring & Control Actions
Update the Risk Register (close the risk with an amplifying note) Return the associated CR to the company (Do not use the reserves to address other risks/issues on the project. CR are used only to handle the impact of the specific risk it was set aside for. They are not a free amount of time or cost that can be used at will by the Project Manager for any needs)
Notes: Agile, Waterfall

## Slide 18: Monitoring & Control Actions in terms of KU & UU
Project Stage | Risk Identified or New | Has the Risk Occurred? | KU or UU | Major Actions
Planning/ Execution | Identified | No | KU | Keep Monitoring
Execution | Identified | Yes | KU | Respond as per plan Expend CR Update Risk Register
Execution | New | No | KU | Analyse the Risk Devise Response Allocate CR Update Risk Register
Execution | New | Yes | UU | Create a workaround Look for any unexpected effects Reevaluate the Identify Risk process Update Risk Register Use MR if approved and released by the management
Notes: Agile, Waterfall