## Slide 1
Lecture 9
Develop Schedule
Notes: Chapter 4
PROJECT integration MANAGEMENT

## Slide 2
  Develop Schedule is the Process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule model.
  The key benefit of this process is that by entering schedule activities, durations, resources, resource availabilities, and logical relationships into the scheduling tool, it generates a schedule model with planned dates for completing project activities..
Develop Schedule
Notes: Chapter 5
PROJECT SCOPE MANAGEMENT
SCOPE MANAGEMENT PLAN
Guidelines for how scope is to be managed and how scope changes are to be integrated into the project
It includes:
  An assessment of the stability of the project scope
  A clear description of how scope changes will be identified and classified

## Slide 3
Schedule Baseline
Project Schedule
Schedule Data
Project Calendars
Project Management Plan updates
Project Documents Updates
____________
Schedule Network Analysis
Critical Path Method
Critical Chain Method
Resource Optimization Techniques
Modeling Techniques
Leads and Lags
Schedule Compression
Scheduling Tools
____________
Schedule Management Plan
Activity List
Activity Attributes
Project Schedule Network Diagrams
Activity Resource Requirements
Resource Calendars
Activity Duration Estimates
Project Scope Statement
Risk Register
Project Staff assignments
Resource Breakdown Structure
Enterprise Environmental Factors
Organizational Process Assets
____________
Inputs
1
Tools and Techniques
2
Outputs
3
Process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule model.
Develop Schedule
Notes: Picture with three text columns
(Intermediate)
To reproduce the picture effects on this slide, do the following:
On the Home tab, in the Slides group, click Layout, and then click Blank.
On the Insert tab, in the Illustrations group, click Picture.
In the Insert Picture dialog box, select a picture and then click Insert.
Select the picture. Under Picture Tools, on the Format tab, in the bottom right corner of the Size group, click the Size and Position dialog box launcher.
In the Size and Position dialog box, on the Size tab, resize or crop the picture as needed so that under Size and rotate, the Height box is set to 1.48” and the Width box is set to 9.17”. Resize the picture under Size and rotate by entering values into the Height and Width boxes. Crop the picture under Crop from by entering values into the Left, Right, Top, and Bottom boxes.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Line Color in the left pane, select Gradient line in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Up (second row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
Also in the Format Shape dialog box, click Line Style in the left pane, and then in the right pane, in the Width box, enter 1 pt.
On the Home tab, in the Drawing group, click Shape Effects, point to Glow, and then do the following:
  Under Glow Variations, select any option in the first row (5 pt glow options).
  Point to More Glow Colors, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Align Center.
To reproduce the first column heading on this slide, do the following:
On the Home tab, in the Drawing group, click Shapes, and then under Rectangles, click Rectangle (first option from the left). On the slide, drag to draw a rectangle.
Under Drawing Tools, on the Format tab, in the Size group, do the following:
  In the Shape Height box, enter 1”.
  In the Shape Width box, enter 2.92”.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Down (first row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 32%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2 (first row, third option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
Also in the Format Shape dialog box, click Line Color in the left pane, select Gradient line in the Line Color pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Up (second row, second option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
Also in the Format Shape dialog box, click Line Style in the left pane. In the right pane, in the Width box, enter 1 pt.
On the Home tab, in the Drawing group, click Shape Effects, point to Glow, and then do the following:
  Under Glow Variations, select any option in the first row (5 pt glow options).
  Point to More Glow Colors, and then under Theme Colors click White, Background 1, Darker 25% (fourth row, first option from the left).
On the slide, right-click the rectangle and then click Edit Text.
Enter text in the text box and select the text. On the Home tab, in the Font group, select Gill Sans MT from the Font list and then select 24 from the Font Size list.
On the Home tab, in the Paragraph group, click Align Text Left to align the text left within the text box.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Tan, Background 2, Darker 75% (fifth row, third option from the left).
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Text Box in the left pane. In the right pane, under Internal margin, enter 1” in the Left box to increase the left margin in the rectangle to accommodate the embossed number.
On the Home tab, in the Drawing group, click Shapes, and then under Lines, click Line (first option from the left).
Press and hold SHIFT, and then on the slide, drag to draw a straight, vertical line.
Under Drawing Tools, on the Format tab, in the Size group, in the Width box, enter 0.75”.
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Line Style in the left pane, and then do the following in the right pane:
  In the Width box, enter 2.25 pt.
  Click the button next to Dash type, and then click Round Dot (second option from the top).
Also in the Format Shapes dialog box, click Line Color in the left pane. In the right pane, click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
On the slide, drag the line onto the rectangle, just left of the text box.
On the Insert tab, in the Text box, click Text Box and then on the slide, drag to draw another text box.
Enter 1 in the text box and select the text. On the Home tab, in the Font group, select Calisto MT from the Font list and then enter 50 in the Font Size box.
On the Home tab, in the Paragraph group, click Center to center the text within the text box.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
Drag the text box onto the rectangle, left of the dotted vertical line.
On the Home tab, in the Editing group, click Select, and then click Selection Pane.
In the Selection and Visibility pane, press and hold CTRL to select the text box, line, and rectangle.
On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Align Middle.
  To reproduce the other column headings on this slide, do the following:
On the Home tab, in the Editing group, click Select, and then click Selection Pane.
In the Selection and Visibility pane, press and hold CTRL to select the text box, line, and rectangle.
On the Home tab, in the Drawing group, click Arrange, and then under Group Objects click Group.
On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate. Repeat the process until you have a total of three groups of shapes.
Select each group in the Selection and Visibility pane and drag it on the slide to form a row under the picture.
Also in the Selection and Visibility pane, press and hold CTRL and select all three groups. On the Home tab, in the Drawing group, click Arrange, point to Align, and then do the following:
  Click Align Middle.
  Click Distribute Horizontally.
  To change the numbers in the duplicate text boxes (second and third from the left), click in each text box and edit the text.
To reproduce the first column (the “subtext” portion) on this slide, do the following:
On the Home tab, in the Drawing group, click Shapes, and then under Rectangles click Rectangle (first option from the left).
On the slide, drag to draw the rectangle so that the top edge is just below the first column heading and the bottom edge is at the bottom of the slide.
Under Drawing Tools, on the Format tab, in the Size group, in the Shape Width box, enter 2.92” so that the subtext column is the same width as the column heading above it.
On the Home tab, in the Drawing group, click the arrow next to Shape Outline, and then click No Outline.
On the Home tab, in the bottom right corner of the Drawing group, click the Format Shape dialog box launcher. In the Format Shape dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Linear.
  Click the button next to Direction, and then click Linear Down (first row, second option from the left).
  Under Gradient stops, click Add or Remove until three stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
    In the Transparency box, enter 100%.
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 50%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2, Darker 25% (third row, third option from the left).
    In the Transparency box, enter 25%.
  Select Stop 3 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
    In the Transparency box, enter 100%.
On the slide, right-click the column and then click Edit Text.
Enter text in the text box and select the text. On the Home tab, in the Font group, select Gill Sans MT from the Font list and then enter 22 in the Font Size box.
On the Home tab, in the Paragraph group, click Center to center the text within the rectangle.
Under Drawing Tools, on the Format tab, in the WordArt Styles group, click the arrow next to Text Fill, and then under Theme Colors click White, Background 1, Darker 50% (sixth row, first option from the left).
On the Home tab, in the bottom-right corner of the Drawing group, click the Format Shapes dialog box launcher. In the Format Shapes dialog box, click Text Box in the left pane. In the right pane, under Text layout, in the Vertical Alignment list, select Top.
To reproduce the other columns (the “subtext” portion) on this slide, do the following:
Select the first “subtext” rectangle. On the Home tab, in the Clipboard group, click the arrow under Paste, and then click Duplicate. Repeat the process until you have a total of three “subtext” rectangles.
Drag each duplicate on the slide to form a row under the “text heading” rectangles.
Press and hold SHIFT and select all three “subtext” rectangles. On the Home tab, in the Drawing group, click Arrange, point to Align, and then click Distribute Horizontally.
To reproduce the background on this slide, do the following:
Right-click the slide background area, and then click Format Background. In the Format Background dialog box, click Fill in the left pane, select Gradient fill in the right pane, and then do the following:
  In the Type list, select Radial.
  Click the button next to Direction, and then click From Center (third option from the left).
  Under Gradient stops, click Add or Remove until two stops appear in the drop-down list.
Also under Gradient stops, customize the gradient stops that you added as follows:
  Select Stop 1 from the list, and then do the following:
    In the Stop position box, enter 0%.
    Click the button next to Color, and then under Theme Colors click White, Background 1 (first row, first option from the left).
  Select Stop 2 from the list, and then do the following:
    In the Stop position box, enter 100%.
    Click the button next to Color, and then under Theme Colors click Tan, Background 2 (first row, third option from the left).

## Slide 4
Develop Schedule

## Slide 5
Schedule Management Plan
Activity List
Activity Attributes
Project Schedule Network Diagrams
Activity Resource Requirements
Resource Calendars
Activity Duration Estimates
Project Scope Statement
Risk Register
Project Staff Assignments
Resource Breakdown Structure
Enterprise Environmental Factors
Organizational Process Assets
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 6
6.6.1.1 Schedule Management Plan
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 7
6.6.1.2 Activity List
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 8
6.6.1.3 Activity Attributes
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 9
6.6.1.4 Project Schedule Network Diagrams
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 10
6.6.1.5 Activity Resource Requirements
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 11
6.6.1.6 Resource Calendars
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 12
6.6.1.7 Activity Duration Estimates
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 13
6.6.1.8 Project Scope Statement
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 14
6.6.1.9 Risk Register
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 15
6.6.1.10 Project Staff Assignments
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 16
6.6.1.11 Resource Breakdown Structure
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 17
6.6.1.12 Enterprise Environmental Factors
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 18
6.6.1.13 Organizational Process Assets
INPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 19
Schedule Network Analysis
Critical Path Method
Critical Chain Method
Resource Optimization Techniques
Modeling Techniques
Leads and Lags
Schedule Compression
Scheduling Tools
Tools & Techniques
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 20
6.6.2.1 Schedule Network Analysis
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 21: Schedule Network Analysis
A technique used by project managers to analyze schedule information and generate realistic and optimal project schedules.
This analysis should be performed upon completion of the draft schedule and network diagram and after each schedule update.
It involves:
Identifying the schedule impact of task dependencies
Identifying critical path tasks and understanding the impact of the critical path on the schedule.
Analyzing the effects of schedule constraints and externally imposed dates
Understanding which tasks can experience delays without delaying the overall schedule
Conducting “what if” analysis of various activity durations (for example, what if the testing activities take twice as long as is currently planned?)
Assessing resource allocation and leveling to prevent resource over-allocation
Assessing fast tracking or crashing options

## Slide 22
6.6.2.4 Resource Optimization Techniques
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 23: Resource Leveling
Resource leveling is the process of changing schedule resource allocation to resolve over-allocations or conflicts. Resource leveling is applied to a schedule that has already been analyzed by the critical path method. This technique is used to adjust a project schedule if shared resources are only available at certain times, or in limited quantities, or if a Project Manager wants to maintain resource usage at a constant level. Resource leveling is often used to correct resource over-allocations and will often change the critical path. The network diagram should be recreated after resource leveling to assess the updated critical path.

## Slide 24
6.6.2.4 Resource Optimization Techniques
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 25
6.6.2.4 Resource Optimization Techniques
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 26
6.6.2.6 Leads and Lags
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 27: Schedule Compression Techniques
As a result of network diagram analysis, project teams may identify a need to compress the schedule. Schedule compression shortens the project schedule in order to meet schedule deadlines without reducing the project scope. Schedule compression techniques include crashing and fast tracking. If utilized, project teams should recreate and reassess the network diagram to ensure that no new schedule issues have emerged.

## Slide 28
6.6.2.7 Schedule Compression
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 29: Crashing
Crashing involves either adding resources or increasing work hours (overtime, weekends) to shorten task duration. Shorter task durations typically result in higher task costs, so project teams must determine, prior to crashing, whether the total costs savings is enough to justify the higher costs. Crashing almost always requires cost increases because it usually necessitates new tasks. Crashing is a controversial technique because adding project resources can increase project complexity or risk and may ultimately have a negative impact on the schedule. Crashing does not involve reducing project scope or eliminating project tasks.

## Slide 30: Fast Tracking
Fast tracking is a schedule compression technique in which project phases or activities usually conducted sequentially are performed in parallel to reduce duration. Care must be taken to ensure that parallel work does not create additional work or increase risk. Fast tracking frequently results in increased complexities in task dependencies, so additional project controls must be implemented to ensure ongoing and accurate insight into schedule performance

## Slide 31
6.6.2.5 Modeling Techniques
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 32: What-If Scenario Analysis
This analysis examines the schedule impact of various scenarios, such as the delayed delivery of a major deliverable. What-if scenario analysis may include simulation that calculates multiple project durations with different sets of activity assumptions. Multiple network diagrams may be generated to visually convey the impact of varying scenarios. Project managers can use the results of this analysis to determine schedule feasibility under adverse conditions and prepare relevant contingency plans

## Slide 33
Critical Path Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 34
Critical Path Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 35: History
Developed in the 1950s by the US Navy
Originally, the critical path method considered only logical dependencies between terminal elements
Since then, it has been expanded to allow for the inclusion of resources related to each activity, through processes called activity-based resource assignments and resource leveling.

## Slide 36: CPM
The Critical Path Method or Critical Path Analysis, is a mathematically based algorithm for scheduling a set of project activities
It is an important tool for effective project management
Commonly used with all forms of projects, including construction, software development, research projects, product development, engineering, and plant maintenance, among others
Any project with interdependent activities can apply this method of scheduling

## Slide 37: CPM
The longest path of planned activities to the end of the project
The earliest and latest that each activity can start and finish without making the project longer
Determines “critical” activities (on the longest path) Prioritize activities for the effective management and to
shorten the planned critical path of a project by:
Pruning critical path activities
“Fast tracking" (performing more activities in parallel)
“Crashing the critical path" (shortening the durations of critical path activities by adding resources)

## Slide 38: Basic Rules for Constructing the Network Diagram
Networks typically flow from left to right.
An activity cannot begin until all of its preceding activities are complete.
Arrows indicate precedence and flow and can cross over each other.
Identify each activity with a unique number.
Looping is not allowed.
Conditional statements are not allowed
Use unique start and stop nodes.

## Slide 39: Definitions
Float(slack)-amount of time that a task can be delayed without causing a delay to:
  subsequent tasks (free float)
  project completion date (total float)
Critical path is the sequence of activities which add up to the longest overall duration. It is the shortest time possible to complete the project. Any delay of an activity on the critical path directly impacts the planned project completion date (there is no float on the critical path). A project can have several, parallel, near critical paths. An additional parallel path through the network with the total durations shorter than the critical path is called a sub-critical or non-critical path.
Critical activity–activity with zero float
Resource leveling – iterative process of assigning crews to activities in order to calculate their duration

## Slide 40
Activity | Duration | Dependency
A | 7 | 
B | 3 | 
C | 6 | A
D | 3 | B
E | 3 | D,F
F | 2 | B
G | 3 | C
H | 2 | E,G

## Slide 41
6.6.2.2 Critical Path Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 42: Developing schedule
We identify the tasks in the Project and specify the resources needed for each one
We allocate to each task sufficient time that we are confident will allow it to be completed with those resources. That is, the time the task should take on average, plus some contingency to give us the confidence we seek
We apply task dependencies, and work out the longest path of tasks in the Project
The time along this path is the Critical of the Project

## Slide 43: Normal practice in the execution phase
As long as every task completes on time (within its contingency), its successors will be started on time
As soon as any task finishes late (outside its contingency), its successors will start late, and this normally means they will finish late
In order to rescue a Project which shows any lateness, we have to squeeze the remaining tasks in the Project
Typically we have to compromise on time, cost or scope and reschedule

## Slide 44: The Estimating Dilemma
If we allow more time for every task in the plan, each task is less likely to be late, but the Project end date will be later...
If we allow less time, the end date will be earlier, but the Project is more likely to overrun
BUT I have to deliver the Project on time

## Slide 45
The dependencies of the activities play an important role in making a project faster or slower and meeting the deadline of the project. You don’t have to be working on the less critical activities when you have most critical ones delaying and pending.
Even the larger projects could be easily handled with the help of critical path method. You don’t have to look at a jumbled and cluttered network; instead, when you have a chart in front of you that is organized, you can make sense of everything and work more efficiently on all the activities.
Working with the floats is another great benefit that critical path method gives to the project manager. When you know that delay in a certain activity wouldn’t affect your project much, you could actually take advantage of this flexibility and work on other critical activities in the meantime.
CPM- ADVANTAGES

## Slide 46
CPM- DISADVANTAGES
The first and the main disadvantage of the technique is its application on more complex and bigger tasks. When you have bigger tasks involving large number of activities, you end up with a big chart which looks more incomprehensible than comprehensible.
Secondly, critical path model is an optimistic model which assumes that all resources will be available at all times and can be utilized whenever they are needed. However, practically this was not always possible. Many times this assumption led to delay in projects and more spending.
In the critical path method, even if an activity is completed before its planned completion date, the time gain cannot be utilized by the next activity, because the next activity has to wait until its early start date. Usually this happens because the resource allocated to the next activity may not be available at the moment. However, the opposite is not true. If any previous activity is delayed, this delay will be passed to the next activity and this may cause delay in the project. In the critical path method, delays accumulate but gain does not
The critical path method is also infected with Student Syndrome, where team members do not start the task until the last moment.

## Slide 47
Critical Chain method
Critical chain method is a modified form of the critical path method. Here, availability of resources is considered while creating the project schedule.
In critical chain project management, instead of float, buffers are used. These buffers are designed in such a way that they completely eliminate the concept of float or slack.
Project Buffer This buffer is placed between the last task and the project completion date as a non-activity buffer, and this buffer acts as a contingency for the critical chain activities. Any delay on the critical chain will eat this buffer, but the project completion date will remain unchanged. Also, if there is any gain from the early finish of any activity, this gain will be added to this buffer as well. Usually the duration of this buffer is 50% of the contingency that you have removed from each task estimate.
Feeding Buffers These buffers are added to the non-critical chain so that any delay on the non-critical chain does not affect the critical chain. They are inserted between the last task on a non-critical chain and the critical chain.
Feeding buffers are also calculated the same way as the project buffer. The duration of these buffers is based on some fraction of the safety removed from the tasks on non-critical chains.
Resource Buffers These buffers are kept alongside the critical chain to make sure that they are available when they are required. This buffer can be a human resource or any equipment. Critical chain considers the resource constraints as well, it may be longer than the critical path schedule. However, this might be compensated by removing the contingencies from the activities. Resources used in critical chain are known as critical resources.

## Slide 48
Critical chain technique

## Slide 49
Remove all contingencies from activities, regardless of whether you have added the calculated contingencies or any percentage of it. If you’ve used
Align the activities with late finish dates and remove resource constraints. Give priority to critical chain activities while assigning resources.
Add feeding buffers to non-critical chains so that their durations become equal to the critical chain. Add project buffer to end of the critical chain, but before the project end date. The project buffer should be approximately half the contingency you removed from the activities. This helps improve the efficiency, and reduces the schedule duration.
How to Create the Critical Chain Network Diagram

## Slide 50
The project based on the critical chain method completes 10% to 30% faster than that based on the critical path method
It is a more practical approach
It encourages team members to perform efficiently
It improves the productivity
CCM- ADVANTAGES

## Slide 51
Critical Chain Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 52
Critical Chain Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 53
Critical Chain Method
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 54
Crashing. Schedule compression technique in which cost and schedule tradeoffs are analyzed to determine how to obtain the greatest amount of compression for the least incremental cost. Crashing does not always produce a viable alternative and can result in increased cost.
Fast tracking. A schedule compression technique in which phases or activities that normally would be done in sequence are performed in parallel. An example would be to construct the foundation for a building before all the architectural drawings are complete. Fast tracking can result in rework and increased risk. This approach can require work to be performed without completed detailed information, such as engineering drawings. It results in trading cost for time, and increases the risk of achieving the shortened project schedule.
Schedule Compression
Develop Schedule
Tools & Techniques

## Slide 55
Scheduling Tools
Develop Schedule
Tools & Techniques
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 56
Schedule Baseline
Project Schedule
Schedule Data
Project Calendars
Project Management Plan Updates
Project Documents Updates
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 57
6.6.3.1 Schedule Baseline
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 58
6.6.3.2 Project Schedule
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 59
6.6.3.2 Project Schedule
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 60
Bar charts. These charts, with bars representing activities, show activity start and end dates, as well as expected durations.
Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces.
Project schedule network diagrams. These diagrams, with activity date information, usually show both the project network logic and the project’s critical path schedule activities.
6.6.3.2 Project Schedule
OUTPUTS
Develop Schedule

## Slide 61
6.6.3.2 Project Schedule
OUTPUTS
Develop Schedule
Reference: Figure 6.21.
PMBOK® Guide, 5th Ed
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 62
6.6.3.3 Schedule Data
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 63
Supporting data for the project schedule includes at least the schedule milestones, schedule activities, activity attributes and documentation of all identified assumptions and constraints. The amount of additional data varies by application area. Information frequently supplied as supporting detail includes, but is not limited to:
    Resource requirements by time period, often in the form of a resource histogram
    Alternative schedules, such as best-case or worst-case, not resource leveled, resource leveled, with or without imposed dates
    Schedule contingency reserves.
6.6.3.3 Schedule Data
OUTPUTS
Develop Schedule

## Slide 64
6.6.3.4 Project Calendars
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 65
6.6.3.5 Project Management Plan Updates
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets

## Slide 66
6.6.3.6 Project Documents Updates
OUTPUTS
Develop Schedule
Notes: Topic 4.1.1
DEVELOP PROJECT CHARTER - INPUTS
4.1.1.1 Project Statement of Work
4.1.1.2 Business Case
4.1.1.3 Agreements
4.1.1.4 Enterprise Environmental Factors
4.1.1.4 Organizational Process Assets