Primavera P6 Project – Report & Deliverables

You have to take any real project preferably of your own organization to complete the given assignment.

Steps:

- Create Project Management Plan

- Create Organizational Structure (OBS)

- Create Enterprise Project Structure (EPS)

- Map OBS with EPS

- Create a Project

- Define Scope (Work Breakdown Structure)

- Assign Responsible Managers on WBS Nodes

- Add Activities (atleast 100)

- Create Relationships

- Add Resources in Resource Dictionary (Atleast 10 Resources Assigned)

- Assign Resources (with ROLES – atleast 2 Roles each for 5x Resources)

- Schedule Project

- Apply Constraints - (Apply a ‘MUST FINISH BY Constraint’ – a week short of planned schedule) + Apply 3 Activity Level Constraints (One must be a “MANDATORY CONSTRAINT”) – Explain in Report

- Optimize Project Plan to finish within time  (Explain in report; Methods + Reasons to Use Methods)

- Make a baseline & Assign to the project

- Update Schedule (Apply Actuals/ Execute Project) based on 8 weeks status update from field (Explain Status Period in the Report).

Grading Criteria:

- Quizzes								(10 Marks)

- Assignments								(10 Marks)

- Class Participation							(10 Marks)

- Project Deliverables (Group of maximum 2 Participants)		(50 Marks)

- Viva Voce 								(20 Marks)

Deliverables of Project:

- ADD Assignment Tasks in the Final Report (PMP, OBS, EPS, WBS, WBS Dictionary etc.)

- Primavera Report (Optimized Planning- Baseline): Baseline Schedule showing "Activity ID, Activity Name, Original Duration, Early Start Date, Early Finish Date, Late Start Date, Late Finish Date, Total Float, Predecessors, Successors in columns" + Early Bars, Late bars, Remaining Bars shall be shown through customize bars.(8 Marks)

- Resource Dictionary Report with Roles & Limits (3 Marks)

- Primavera Report (Execution): Updated Schedule showing "Activity ID, Activity, Original Duration, Baseline Start Date, Baseline Finish Date, Start Date, Finish Date, Total Float, Schedule % Complete, Units % Complete, Physical % Complete"+ Project Baseline Bar, Actual Bar, and Remaining bars shall be shown through customize bars. Extract a Report (10 Marks). Earned Value Method selection must be explained in the report with screen shot.

- Primavera Report (Time Scaled Logic Diagram – with Baseline & Current Bars) (5 Marks)

- Primavera Reports (S-Curve):

  - After Execution; generate report “S-Curve with Resource Loading Units”             (5 Marks)

  - Generate report of “Earned Value Costs” (5 Marks).

- Extract Project Website from Primavera, showing ‘updated schedule’ and 2 reports of your choice. (2 Marks)

- Primavera Report (Add & Customize a Primavera Visualizer Report by Showing Activities with Steps, Baseline Bars, Actual Bars, Remaining Bars, Bar Labels, Relationships, Milestones, Background) (7 Marks)

Deliverables Total:

- 2 Project files XER format (1 baseline, 1 after updated schedule) – (Soft Copy)

- 11 Reports from Primavera – (Soft Copy + Hard Copy)

- 1 Document (Project Report with Project Management Plan) – (Soft Copy + Hard Copy)

Report Preparation: (5 Marks for Mandatory Inclusions Listed Above)

- (Prepare a Project Report containing Chapters:

  - Table of Contents (Generated), Introduction, Project Management Plan, Planning & Scheduling, Monitoring & Control, Execution, Earned Value/ Performance Management) – Not less than 50 Pages

All the deliverables (soft copies in a CD; marked with participants’ Enrollment No., and Hard Copy in the form of Binded Report) may be submitted to Ms. Nayyer (Student Advisor MSPM).

DEADLINE:

- Submission by Monday, December 26, 2016 1400 hours

- Schedule for Viva Voce will be communicated later (~ 1 week after Exams)